Abstract from TI NOSC Technical Report

Full Technical Report is Available from the DoD Ada Software Repository

on SIMTEL20

Prepared by Richard Conn, TI Ada Technology Branch, 26 Sep 85

CHAPTER 3

SOFTWARE PRODUCTIVITY INFORMATION

In this chapter, Texas Instruments reports on  Software  life

cycle  labor  distribution  (as gathered from our labor collection

system), productivity (LOC) and experiences with software reuse.

< Detail Omitted >

3.2  SOFTWARE LIFE CYCLE LABOR DISTRIBUTION

In order that proper  tracking  of  project  hours  could  be

accomplished, we established labor categories reflective of the SW

life cycle within our labor reporting system.   As  the  engineers

advanced  thru  the  life  cycle,  time  was charged to the charge

number corresponding to the phase.  Analysis of the data indicates

hours  were  spent  as  follows.  Several numbers in this data may

appear suspect; this is how the  labor  system  recorded  it;  the

accuracy  of  this data is subject to the normal problem of humans

inputting the correct data.

Virtual  | Spelling  |   Style  |  Batch/Forms

Terminal | Corrector |  Checker |   Generator

======== | ========= |  ======= |  ===========

Requirements                 |           |          |

System Spec                  |   11   1% |          |

Preliminary Design           |  458  30% | 416  28% |   397  29%

Users manual         16   1% |  100   7% |  35   2% |    35   3%

Detailed design     344  20% |   40   3% | 148  10% |   223  16%

Implementation      634  37% |  604  40% | 517  35% |   559  40%

Training              8   0% |    8   1% |  12   1% |     8   1%

Integration                  |           |          |     4   0%

Qaulity Assurance    26   2% |           |          |

Testing             594  35% |  226  15% | 273  18% |    79   6%

Data management       4   0% |           |          |

Configuration Mgt     1   0% |    3   0% |   3   0% |     1   0%

------------------           |           |          |

Sub Total          1627      | 1450      |1404      |  1306

Program Management   76   4% |   76   5% |  75   5% |    75   5%

------------------           |           |          |

Grand Total        1703      | 1526      |1479      |  1381

Manmonths          9.84      | 8.82      |8.58      |  7.98

* Note: Percentages do not total to 100% due to roundoff errors

While a manmonth is contractually approximated at 173  hours,

many hours in excess of an 8 hour day were worked.

Since this program was managed as  1  contract  with  4  task

elements, program management time was accumulated as an aggregate;

the hours spent are allocatable to the whole program, not any  one

tool  in  particular.  Total program management hours was 303.  In

the above table, these hours were allocated  equally  across  each

tool.

Requirements and  System  specification  had  little  charges

because  the  proposals  written for these tools were written with

the intent that they serve as the requirements and  specifications

documents

Configuration management  is  low  because  some  of  the  CM

function  was  handled  by  a support group (not allocated to this

project) and some was accomplished after the  data  was  extracted

for  this  report.   In  any case, all Software and documents have

been CM'd and a retrievable according to standard TI procedures.

3.3  PRODUCTIVITY (LOC)

TI used the PAGER tool from the Ada repository as  a  vehicle

by which to count Ada statements, comments and total text lines in

the tools.  This tool considers an Ada statement to be  terminated

by a semicolon.  As such, a text line can contain one Ada comment,

one or more Ada statements, or one or more Ada statements  and  an

Ada comment.

Following is a table indicating  the  lines  of  Ada  source,

comments,  text  lines  and  testing  code  in  each  of the tools

written.  Note that in the batch/form generator  and  the  virtual

terminal,  testing  code had to be written to exercise the various

interfaces; this code was also written in Ada.

Virtual     Spelling       Style         Batch/Forms

Terminal    Corrector     Checker         Generator

========    =========     =======        ===========

Ada Source:     2421        2743          3189          2869

Comments:        590        2626          2013          1707

Text Lines:     6300        9458          9762          8307

Test Source     1218                                     163

Comments:        155                                     200

Text Lines:     1762                                    1398

---------

Totals:

Ada Source:   3639        2743          3189          3032

Comments:      745        2626          2013          1907

Text Lines:   8062        9458          9762          9705

Any figures regarding lines of code/day must consider the way

lines  of  code is determined.  Some techiques consider every text

line in a program to be a line  for  measurement  purpose,  others

only  count  executable  statements  and exclude comments and data

definition.  Since there seems to be no universal agreement on the

proper technique, for the purposes of this report, we will compute

LOC based on both the total number of text  lines  and  the  total

number  of Ada source statements.  In all cases, testing code will

be counted.

Virtual     Spelling       Style         Batch/Forms

Terminal    Corrector     Checker         Generator

========    =========     =======        ===========

Ada Source:     3639        2743          3189          3032

manmonths        9.84        8.82          8.55          7.98

LOC/mm         369.8       311.0         372.98        379.9

LOC/day         17.2        14.46         17.34         17.67

Text Lines:     8062        9458          9762          9705

manmonths        9.84        8.82          8.55          7.98

LOC/mm         819.3      1072.3        1141.75       1216.16

LOC/day         38.13       49.87         53.10         56.56

LOC/day assumes 21.5 work days per month.  It should be noted

that  these  tools did require some Mil-Std documentation, such as

design specs, test plans/procedures, users manuals.  Where nothing

was mandated in the CDRL list, internal TI documentation standards

were used.

Output Data from the Manpower Projection Tool, a NOSC Tool created by

GTE West

The following charts and tables show projected manpower staffing based

on the Cocomo model in Semidetached mode.  The data is based on the Line

of Code count from each of the four NOSC tools.  Compare the projected

staffing with the actual staffing which was required.  Only the nominal

schedule is shown.

1. MANPOWER Projection Report for Virtual Terminal

Boehm / DeMarco / Estimated Staffing Profiles

Lines of source code in thousands (KSLOC) =     8.0620

Man-months of effort

(equation from Barry W. Boehm, pg.75, table 6-1) =    31.0697

Most likely delivery time

(equation from Barry W. Boehm, pg.75, table 601) =     8.3226

The impossible region

(equation from Tom DeMarco, pg.181) =   5.973 months or less

Equation mode type used: SEMIDETACHED

Nominal     Schedule

--------------------

**********     Acceleration rate =   0.033

*****   Peak staffing occurs around month   3.9     **********

Staffing Estimate:                                         Month      Est. Staff

-----     ----------

5 |  **                                                 1         1.98404

4 | *  **                                               2         3.59405

3 |      *                                              3         4.57106

2 |*      *                                             4         4.83764

1 |                                                     5         4.49323

+--------                                             6         3.75051

0  3  6                                               7         2.84921

Duration (months)                          8         1.98491

2. MANPOWER Projection for Spelling Corrector

Boehm / DeMarco / Estimated Staffing Profiles

Lines of source code in thousands (KSLOC) =     9.4580

Man-months of effort

(equation from Barry W. Boehm, pg.75, table 6-1) =    37.1549

Most likely delivery time

(equation from Barry W. Boehm, pg.75, table 601) =     8.8602

The impossible region

(equation from Tom DeMarco, pg.181) =   6.340 months or less

Equation mode type used: SEMIDETACHED

Nominal     Schedule

--------------------

**********     Acceleration rate =   0.028

*****   Peak staffing occurs around month   4.2     **********

Staffing Estimate:                                         Month      Est. Staff

-----     ----------

5 |  ****                                               1         2.02323

4 | *    *                                              2         3.72043

3 |       *                                             3         4.85158

2 |*       *                                            4         5.31742

1 |                                                     5         5.16617

+---------                                            6         4.55603

0  3  6  9                                            7         3.69361

Duration (months)                          8         2.77357

9         1.93851

3. MANPOWER Projection for Style Checker

Boehm / DeMarco / Estimated Staffing Profiles

Lines of source code in thousands (KSLOC) =     9.7620

Man-months of effort

(equation from Barry W. Boehm, pg.75, table 6-1) =    38.4950

Most likely delivery time

(equation from Barry W. Boehm, pg.75, table 601) =     8.9708

The impossible region

(equation from Tom DeMarco, pg.181) =   6.415 months or less

Equation mode type used: SEMIDETACHED

Nominal     Schedule

--------------------

**********     Acceleration rate =   0.029

*****   Peak staffing occurs around month   4.2     **********

Staffing Estimate:                                         Month      Est. Staff

-----     ----------

6 |   *                                                 1         2.16889

5 |  * **                                               2         3.97635

4 | *    *                                              3         5.15945

3 |       *                                             4         5.61539

2 |*       *                                            5         5.40679

1 |                                                     6         4.71607

+---------                                            7         3.77397

0  3  6  9                                            8         2.79172

Duration (months)                          9         1.91830

4. MANPOWER Projection for Batch/Forms Generator

Boehm / DeMarco / Estimated Staffing Profiles

Lines of source code in thousands (KSLOC) =     9.7050

Man-months of effort

(equation from Barry W. Boehm, pg.75, table 6-1) =    38.2434

Most likely delivery time

(equation from Barry W. Boehm, pg.75, table 601) =     8.9502

The impossible region

(equation from Tom DeMarco, pg.181) =   6.401 months or less

Equation mode type used: SEMIDETACHED

Nominal     Schedule

--------------------

**********     Acceleration rate =   0.028

*****   Peak staffing occurs around month   4.2     **********

Staffing Estimate:                                         Month      Est. Staff

-----     ----------

5 |  ****                                               1         2.08250

4 | *    *                                              2         3.82942

3 |       *                                             3         4.99371

2 |*       *                                            4         5.47319

1 |                                                     5         5.31751

+---------                                            6         4.68950

0  3  6  9                                            7         3.80181

Duration (months)                          8         2.85482

9         1.99529

####################